## Sheet1
Activity | Expected Start Date | Expected end date | Actual Start Date | Actual end date
SRS Release | 13th October | 18th October | 13th October | 19th October
Design | 14th October | 14th October | 14th October | 14th October
Coding | 15th October | 15th October | 15th October | 15th October
UT Plan | 16th October | 17th October | 16th October | 17th October
UT | 16th October | 17th October | 16th October | 17th October
IT Plan | 17th October | 18th October | 17th October | 18th October
IT | 18th October | 18th October | 18th October | 18th October
Sprint Demo | 19th October | 19th October | 19th October | 19th October